## Trang tính1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 2022-05-28 | 2022-06-06 | 98% | Long
Carousel | 2022-05-28 | 2022-05-28 | 100% | Long
Choose | 2022-05-30 | 2022-06-02 | 100% | Long
About,Statistic | 2022-05-30 | 2022-06-02 | 100% | Long
Commit | 2022-05-30 | 2022-06-04 | 100% | Long
Solutions | 2022-05-30 | 2022-06-04 | 100% | Long
Questions |  |  |  | Hữu
Projects |  |  |  | Hữu
Testimonials |  |  |  | Hữu
Community |  |  |  | Hữu
Footer |  |  |  | Hữu